## Analysis
|  | Risk | Integration | Cost | SMBR Opportunity | Vendor Participation | Time to Market
1 | One RFP for both VFTU and Employee Safety | 4 | 4 | 3 | 3 | 3 | 4
2 | VFTU Separate from Employee Safety | 2 | 2 | 2 | 4 | 3 | 2
3 | Separate VFTU Hardware and Software | 3 | 3 | 4 | 4 | 4 | 4
1 | One vendor RFP to bid on the entire work - both VFTU and Employee Safety database | Least risk - one vendor responsible | One vendor yields better integration | Software vendor likely to subcontract to hardware vendor increasing cost | Lesser SMBR opportunity with one RFP | Some software vendors may not be able or willing to deal with hardened devices | One accountable vendor more likely to provide a quicker solution
2 | Separates project into two RFPs - one for VFTU and another for Employee Safety database | Higher risk of successful integration with multiple vendors | Higher risk of successful integration with multiple vendors - potentially requires internal integration | Higher cost because additional integration required plus potential of two user licenses in vehicle | Higher SMBR opportunity - multiple RFPs | Some software vendors may not be able or willing to deal with hardened devices | Additional time required to integrate separate solutions - requires CTM scheduled support for ESB development
3 | Separates VFTU hardware and installation as a separate RFP from the software development activity for both VFTU and Employee Safety | Some risk because software vendor does not select hardware platform | Some integration issues because software vendor does not select hardware platform | Lowest cost - no subcontracting pass through | Higher SMBR opportunity - multiple RFPs | In line with most vendor's specialties | Although separate vendors, their critical path is relatively straight forward and not likely to impede each other’s progress