## Slide 1: Rob Byrd
SOA Infrastructure Status

## Slide 2: Overall SOA Strategy
Obtain competent staff augmentation
  Brings experience to initially lead ESB effort and mentor city staff
Hire competent staff
  Must have skills and abilities to learn ESB
Complete pilot interface
  IBM contributed 132 hours to install, configure and employ first pilot interface

## Slide 3: Risk Items
Risk Item 01:
  Obtain three 2 Core virtual devices – ESG plans to support
Risk Item 02:
  Funding – we're currently short ~$80K. Funding is needed to obtain competent staff augmentation and hire competent staff. IBM is providing 132 hours of lab services; however, unknown complexity of the interface may lead to an incomplete solution. Therefore, we're recommending to synchronize staff augmentation/new hire timing with IBM Lab support, so the new staff will be knowledgeable enough to complete the interface if IBM Lab resources run short

## Slide 4: Risk Items (continued)
Risk Item 03:
  Hire competent staff. Our current salary-base does not provide enough expected salary to attract skilled and competent ESB developers – existing internal skilled resources identified
Risk Item 04:
  Obtain competent staff augmentation. Our selection of IIB (essentially WebSphere Message Broker), reduced this risk significantly. We're obtaining qualified resumes interested in the position
Risk Item 05:
  CSR AppHub interface complexity. The 132 hours provided by IBM does not guarantee a successful working interface. To reduce this risk we negotiating with IBM to delay the interface pilot until we are staffed (April timeframe)

## Slide 5: Risk Items (continued)
Risk Item 06:
  Test environment for CSR/IIB/Maximo interface development. Test environment is planned to be ready